## Status
Consistency checker: where things stand
Status as discussed in this conversation. 'Checked' items were read by a person, not by a program.
Part | State | Notes
Fact sheet format (YAML template) | Written | Lives in the general (layer 1) prompt file.
Fact sheets themselves | Written by hand / generated | Each of the five demos ends with a hand-written sheet; a few were generated with DeepSeek.
Automatic check script (evaluator) | NOT written | The 'programmable checks' list in the generation prompt file is a design only.
Validation that the checks work | NOT done | No false-alarm test, no injected-error test, no run on the DeepSeek versions.
All checking so far | By eye | Dose plan comparison and English/Chinese comparison were read by a person; reading dozens of numbers by eye is unreliable.
Feedback inside the web page | Hand-written | Feedback text was written into the page, not computed from the fact sheet.
Fact-sheet table inside the web page | Hand-filled | Not linked to a data file.
README line 'no automated consistency checker yet' | Still true | Keep until the script exists and is validated.

## Checks v0
Planned v0 checks (programmable only)
# | Check | What is compared | Compared against | Automatable now? | Status
1 | All 12 sections present | Section headings (including 10.1 to 10.5) in the document | Document skeleton in the general prompt file | Yes | Not written
2 | Dates in chronological order | All dates in the document | Timeline in the fact sheet | Yes | Not written
3 | Doses and scores match | Doses and scale scores quoted in the document | Fact sheet (doses, severity scores) | Yes | Not written
4 | Left/right consistent | Side of lesion or findings across documents | Fact sheet (lesion location) | Yes | Not written
5 | Final diagnosis not listed as excluded | Excluded differentials list | Fact sheet (diagnosis, differential) | Yes | Not written
6 | Tetrabenazine titration follows guidance | Week-by-week dose plan | Guideline layer, huntington/treatment file | Yes | Not written

## Validation plan
How to prove the checks work
Legend: yellow cells are for you to fill in (Y or N in 'Caught?'; counts in the false-alarm block). Example row below is not counted.
Step | Test | What it measures | Expected result | Status
1 | Run the checker on the current demos | False alarms (does it flag correct text?) | Demos pass with no flags | Not run
2 | Copy the demos and inject known errors | Detection rate (does it catch wrong text?) | Each injected error is flagged | Not run
3 | Run on the two DeepSeek versions (with / without guidance layer) | Whether the script finds the layer difference without a person reading | Missing genotyping requirement flagged in one version | Not run
Injected-error log
Error type | Example change | Check that should catch it | Caught? (Y/N) | Notes
Example (not counted): date moved | Follow-up visit dated before the surgery | Check 2 | Y | Format example only
Lesion size changed | 3.8 cm changed to 4.2 cm in one document | Check 3
Laterality flipped | Left changed to right | Check 4
Date moved earlier | Event dated before the previous event | Check 2
Wrong dose | Dose changed in one place only | Check 3
Summary
Errors injected | 4
Errors caught (Y) | 0
Detection rate | not run yet
Demos tested (step 1)
False alarms in step 1
False alarms per demo | not run yet
Assumption: detection rate counts only the rows listed above; add more rows inside the yellow range to widen the test.

## Limits and fixes
What the checker cannot do, and one wording fix
Limit | Explanation | How to word it
Consistent but clinically wrong | The checker only compares text with the fact sheet and written rules. The imaging problem in the Huntington demo was fully consistent, yet clinically unreasonable. | Say 'consistency and traceability', not 'guaranteed correct content'.
Application wording fix (lay summary, third paragraph)
Version | Sentence | Characters
Current (reads as if the program already exists) | a computer program checks that the content is consistent and matches published sources | 86
Proposed (future tense) | a computer program will check that the content is consistent and matches published sources | 90
Characters added |  | 4
Lay summary total after fix (was 1,818 of 3,000) |  | 1822
Assumptions: 1,818 is the lay summary count measured earlier with a program. If the Google Doc or the form is already updated, change the same sentence in both places.
Scientific summary: 'Build automated checks' is already a future action, so no change is needed there.